## Sheet1
Chanllenge in my dream company
Activity | Description | Dependence
A | Cutting for machining | -
B | Machining | A
C | Assembly 1 | B
D | Disassembly 1 | C
E | Painting | B, C, D
F | Assembly 2 | E
G | Assembly 3 | F
H | Assembly 4 | G
I | Quality | E, F, G
J | Packing | I
K | Shipment | J
Activity | Normal Duration | Acc. Duration | Normal Cost | Accelerated Cost | Increase in cost
A | 4 | 2 | 45 | 100 | 55
B | 12 | 8 | 130 | 230 | 100
C | 14 | 10 | 270 | 430 | 160
D | 3 | 1 | 180 | 290 | 110
E | 10 | 5 | 150 | 350 | 200
F | 14 | 10 | 90 | 135 | 45
G | 15 | 11 | 85 | 156 | 71
H | 16 | 13 | 145 | 189 | 44
I | 12 | 8 | 189 | 258 | 69
J | 2 | 1 | 190 | 344 | 154
K | 1 | 0.5 | 890 | 1000 | 110
Total | 103 | 69.5 | 2364 | 3482 | 1118
Total increase in cost of the project |  | 1118